## Documentation
DOCUMENTATION PHASE
STEP | DESCRIPTION | STATUS | DURATION (HOURS)
DONE
IN PROGRESS
PENDING
1. List all functionalities and requirements previously defined | Create the list based on business requirements and documents such as Final Report Agile Inception | DONE | 1
2. Sequence the functionalities in order of priority based on: | What the Web2 team needs to integrate and test first. I.e. Calculate number of tokens to return | DONE | 1
| What is required to integrate with external interactions. I.e. Oracle data feeds, other crypto tokens interfaces | DONE
| What is the core functionality of the development. I.e. Buy a token | DONE
3. Create the initial UML diagram with all the constants, variables, modifiers, events and functionalities you consider necessary. | Functionalities | DONE | 3
| Variables & structs | DONE
| Constants | DONE
| Constructor | DONE
| Modifiers | DONE
| Events | DONE
4. Create the initial documentation, using the Documentation Format, describing for each use case (functionality): | Title | PENDING | 3
Description
Actors and interfaces
Initial status and preconditions
Post Condition
Alternative flows
5. Research any tool or platform required to interact with the smart contract and identify any additional requirements. | I.e. On ramp FIAT-Crypto platforms, multi signature wallets, oracles, etc. | DONE | 3

## Development
DEVELOPMENT PHASE
STEP | DESCRIPTION | STATUS | DURATION (HOURS)
DONE
IN PROGRESS
PENDING
1. Create a repository (GitHub/Gitlab) to upload the code | https://github.com/login https://gitlab.com/users/sign_in | DONE
2. Clone the Scaffold ETH repository and use the Hardhat Framework to develop the first local version | https://github.com/scaffold-eth/scaffold-eth-2 | DONE
3. Create a ToDo list to track the tasks you are still pending to do | You can even use a Notepad app | PENDING
4. Develop the Smart contract | Code the variables from the UML diagram | PENDING
| Code the functions from the UML diagram | PENDING
| Code the modifiers from the UML diagram | PENDING
| Code the events from the UML diagram | PENDING
| Add any required modification to the code | PENDING
5. Once you are finished, use ChatGPT to add documentation line by line inside of the methods. Use the prompt: "Add comments inside of the code for each line of the following solidity code:" | https://chat.openai.com/auth/login | PENDING
6. Use ChatGPT once again to add Natspec documentation to the methods and functionalities. Use the prompt: "Edit the following solidity code to add in Natspec comments: " | https://chat.openai.com/auth/login | PENDING
7. Add the Basic Flow detailed steps to finish the documentation | https://chat.openai.com/auth/login | PENDING

## Good practices
GOOD PRACTICES PHASE
VULNERABILITIES TO BE AWARE | DESCRIPTION | STATUS | DURATION (HOURS)
DONE
IN PROGRESS
PENDING
1. ABI Hash Collisions - Smart contract | Be aware of the use of abi.encodePacked | PENDING
2. Ambiguous Evaluation Order - Smart contract | Use parenthesis and variables to store values of long functions | PENDING
3. Approval Vulnerabilities - Frontend | Perform Ethical Hacking | PENDING
4. Exposed Data - Project | Don't upload Personal Identifiable Information to the blockchain | PENDING
5. Frontrunning | Out of scope (for now) | PENDING
6. Griefing - Smart contract | Delayed withdrawal of funds with timestamp | PENDING
7. Gas Griefing Attacks - Smart contract | Check the successful execution of external smart contract calls | PENDING
8. Incorrect Parameter Order - Smart contract | Check the order of parameters that arrive in the functions | PENDING
9. Oracle Manipulation - Smart contract | Use Chainlink | PENDING
10. Reentrancy - Smart contract | Use ReentrancyGuard on withdrawal functions | PENDING
11. Signature-related Attacks - Smart contract | Be aware of the use of ECDSA ¦ and signatures | PENDING
12. Unexpected Ether Transfers - Smart contract | Be aware of the functions that receive ether like payable and receive | PENDING
13. Unsafe private key storage - Backend | Follow best practices for Private key management | PENDING
READ AGAIN FOR NEW VULNERABILITY UPDATES | https://scsfg.io/developers/testing/ | PENDING
Document new findings in your development process and ask to add it to this guide. | This document | PENDING

## Resources & Links
RESOURCES & LINKS
RESOURCE | LINK
Scaffold ETH | https://github.com/scaffold-eth/scaffold-eth-2
(Ethereum) Sepolia Faucet to obtain testnet ETH | https://sepoliafaucet.com/
(Polygon) Mumbai Faucet to obtain testnet ETH | https://mumbaifaucet.com/
Polygonscan API KEY to be able to verify smart contracts | https://polygonscan.com/login
Etherscan API KEY to be able to verify smart contracts | https://etherscan.io/login
Ether, Gwei, Wei Calculator and Converter | https://www.alchemy.com/gwei-calculator
Solidity scan for Smart contract audit | https://solidityscan.com/home
Chainlist to identify RPC blockchain networks | https://chainlist.org/?search=
Dates and time operations documentation | https://soliditytips.com/articles/solidity-dates-time-operations/
SAFE wallet multisig | https://safe.global/
Price feed contract addresses Chainlink Oracle | https://docs.chain.link/data-feeds/price-feeds/addresses?network=ethereum&page=1
Pinata IPFS service | https://app.pinata.cloud/signin
CRYPTO TOKEN ADDRESSES OVER REAL POLYGON
MATIC | Native token of the blockchain
USDC | 0x3c499c542cef5e3811e1192ce70d8cc03d5c3359
USDT | 0xc2132d05d31c914a87c6611c10748aeb04b58e8f
WBTC | 0x1bfd67037b42cf73acf2047067bd4f2c47d9bfd6
WETH | 0x7ceb23fd6bc0add59e62ac25578270cff1b9f619
ORACLE PRICE DATA FEED BY CHAINLINK OVER REAL POLYGON
MATIC/USD | 0xAB594600376Ec9fD91F8e885dADF0CE036862dE0
USDC/USD | 0xfE4A8cc5b5B2366C1B58Bea3858e81843581b2F7
USDT/USD | 0x0A6513e40db6EB1b165753AD52E80663aeA50545
WBTC/USD | 0xDE31F8bFBD8c84b5360CFACCa3539B938dd78ae6
WETH/USD | 0xF9680D99D6C9589e2a93a78A04A279e509205945